## breakdown cmd
Samsung BBU Emulation
Feature |  |  | O/X for SS BBU-E (O : support, X: Not support) | Reference Doc. | Market priority (1, 2,3… ) | Remark
Installation Verification | Initialization | Initialization Notification | O | 3.1.3 |  | Initialization Information IE(FW Mode-User Mode, Cascade Id, FW version, RIMS Version)
|  |  | O | 3.1.4 |  | Initialization Acknowledge Information IE(System Id-LTE, Alarm Acknowledge)
|  | RU ID Acquisition | O | 3.1.1 / 3.1.2 |  | RU ID Configuration IE(RU ID, Cascade ID, Base IP Address, Serial Number, RU Board Name, Tree ID)
| Configuration Setup | System Configuration Setup | O | 3.8.1 |  | System Configuration IE(Valid Num of FA, RS/RP mode, Split Mode, Measure Report Period, Ref Clock Mode)
|  |  | O |  |  | RU Port Control IE(Port ID - RU Port ID, Port Type - UDE Port, Port enable/disable)
|  |  | O |  |  | PIM Detection and Cancellation On/Off IE(PIM Detection and Cancellation On/Off)
|  |  | O |  |  | Rx only Antenna Port VSWR Monitoring On/Off IE(Rx only Port VSWR Monitoring On/Off)
|  |  | O |  |  | Rx only Antenna Port VSWR Monitoring Configuration IE(Monitoring Period, VSWR FAIL MJ Threshold for Rx only Antenna Port
|  |  | O |  |  | PIM Detection and Cancellation algorithm setup IE(PIM algorithm - intra/inter band PIM)
|  |  | ? |  |  | DMTC IE(dmtc(Discovery signal Measurement Timing Configuration) periodicity, dmtc offset)
|  | FA Configuration Setup | O | 3.8.3 |  | FA Configuration IE(Admin Status, Service Type - FDD LTE, Bandwidth, DL Max Power, Tx Frequency, Rx Frequency, Mapping Tx Path Id(0~31), Mapping Rx Path Id(0~31), Mapping RU CPRI Id, CPRI Channel Id, Base Station System Id, NB-IoT Cell Status, NB-IoT Mode, Mapping Tx Path Id(32~63), Mapping Rx Path Id(32~63))
|  |  | O |  |  | FA/Path Configuration IE(Tx Atten, Rx Atten)
|  |  | O |  |  | FA CPRI Channel Configuration IE(Tx CPRI Channel Id, Rx CPRI Channel Id)
|  |  | O |  |  | Cascade FA CPRI Channel Configuration IE(CPRI Id connected with previous hop, Tx CPRI Channel Id received from previous hop, Rx CPRI Channel Id received from previous hop, CPRI Id connected with next hop, Tx CPRI Channel Id sending to next hop, Rx CPRI Channel Id sending to next hop, Service Type, Bandwidth, Tx antenna count, Rx antenna count)
|  |  | O |  |  | FA Modulation Information IE(Modulation Information - 64 QAM/256 QAM)
|  |  | ? |  |  | NB-IoT Configuration IE(NB-IoT Tx Frequency, NB-IoT Rx Frequency, NB-IoT UL Dividing, NB-IoT DL Combining)
|  | Path Configuration Setup | O | 3.8.5 |  | Path Configuration IE(Start Frequency, Tx Atten, Rx Atten)
|  |  | O |  |  | Antenna Port Control per Path IE(Antenna Port Role - Antenna Port + ALD pwer feeding / AISG signal) Bias-T
|  | CPRI Configuration Setup | O | 3.8.7 |  | CPRI Configuration IE(IQ Mapping)
|  |  | ? |  |  | CPRI Compression IE(CPRI Compression On/Off, CPRI Compression Ratio)
|  |  | ? |  |  | CPRI Connection Check IE(Branch Id)
|  | Tx FA/Path On/Off | O | 3.3.1 |  | FA/Path On/Off IE(Tx Path On/Off, Rx Path On/Off)
|  | Path Enable/Disable | O | 3.3.3 |  | Path Control IE(Path Enable/Disable)
|  | Alarm Threshold Setup | O | 3.4.5 |  | Alarm Threshold IE(Alarm Code, Alarm Subcode Type, Alarm Subcode, Alarm Severity, Alarm Declare Threshold Value, Alarm Clear Threshold Value)
|  | Delay Setup | O | 3.10.1 |  | Delay Value IE(Tx Delay, Rx Delay)
|  | Time Sync | O | 3.11.1 |  | Time Tick IE(Time Tick, Time Tick Offset, Daylight Saving Time)
|  | Power Boost Setup | O | 3.16.1 |  | Boost Level IE(Power Boost Level)
| Get Information | Firmware Information | O | 3.6.11 / 3.6.12 |  | F/W Information IE(Running F/W version, Saved F/W version, Running F/W Build Date, Saved F/W Build Date, Vendor)
|  | Hardware Information | O | 3.7.1 / 3.7.2 |  | H/W Version IE(H/W Version)
|  |  | O |  |  | H/W Description IE(Description)
|  | System Configuration Get | O | 3.2.1 / 3.2.2 |  | System Configuration IE(Valid Num of FA, RS/RP mode, Split Mode, Measure Report Period, Ref Clock Mode)
|  |  | O |  |  | RU Port Control IE(Port ID - RU Port ID, Port Type - UDE Port, Port enable/disable)
|  |  | O |  |  | PIM Detection and Cancellation On/Off IE(PIM Detection and Cancellation On/Off)
|  |  | O |  |  | Rx only Antenna Port VSWR Monitoring On/Off IE(Rx only Port VSWR Monitoring On/Off)
|  |  | O |  |  | Rx only Antenna Port VSWR Monitoring Configuration IE(Monitoring Period, VSWR FAIL MJ Threshold for Rx only Antenna Port
|  |  | O |  |  | PIM Detection and Cancellation algorithm setup IE(PIM algorithm - intra/inter band PIM)
|  |  | ? |  |  | DMTC IE(dmtc(Discovery signal Measurement Timing Configuration) periodicity, dmtc offset)
|  | System Status | O | 3.2.3 / 3.2.4 |  | System Status IE(RU Initial status, Cascade Id, Multi Mode, FW Mode, System Temperature, RIMS Version, Supported OFR Start Frequency, Supported OFR Bandwidth, Supported IBW Bandwidth, DC Input Voltage, DC Output Voltage, Tx Filter Center Frequency, Rx Filter Center Frequency, Tx Filter Bandwidth, Rx Filter Bandwidth, Battery Equipment Status, FAN Equipment Status, FAN1~4 Speed, Tree ID)
|  |  | O |  |  | Time Tick IE(Time Tick, Time Tick Offset, Daylight Saving Time)
|  |  | O |  |  | Measured Power IE(Measured Power)
|  | FA Configuration Get | O | 3.2.5 / 3.2.6 |  | FA Configuration IE(Admin Status, Service Type - FDD LTE, Bandwidth, DL Max Power, Tx Frequency, Rx Frequency, Mapping Tx Path Id(0~31), Mapping Rx Path Id(0~31), Mapping RU CPRI Id, CPRI Channel Id, Base Station System Id, NB-IoT Cell Status, NB-IoT Mode, Mapping Tx Path Id(32~63), Mapping Rx Path Id(32~63))
|  |  | O |  |  | Boost Level IE(Power Boost Level)
|  |  | O |  |  | FA/Path Configuration IE(Tx Atten, Rx Atten)
|  |  | O |  |  | FA/Path On/Off IE(Tx Path On/Off, Rx Path On/Off)
|  |  | O |  |  | FA CPRI Channel Configuration IE(Tx CPRI Channel Id, Rx CPRI Channel Id)
|  |  | O |  |  | Cascade FA CPRI Channel Configuration IE(CPRI Id connected with previous hop, Tx CPRI Channel Id received from previous hop, Rx CPRI Channel Id received from previous hop, CPRI Id connected with next hop, Tx CPRI Channel Id sending to next hop, Rx CPRI Channel Id sending to next hop, Service Type, Bandwidth, Tx antenna count, Rx antenna count)
|  |  | O |  |  | FA Modulation Information IE(Modulation Information - 64 QAM/256 QAM)
|  |  | ? |  |  | NB-IoT Configuration IE(NB-IoT Tx Frequency, NB-IoT Rx Frequency, NB-IoT UL Dividing, NB-IoT DL Combining)
|  |  | O |  |  | Cell Status Information IE(Cell Status - enable)
|  |  | O |  |  | Scale Factor per FA IE(Scale Factor, Last flag)
|  | FA Status | O | 3.2.7 / 3.2.8 |  | FA/Path Status IE(Output Level)
|  |  | O |  |  | TSSI/RSSI IE(RSSI, TSSI Digital IQ Level, RSSI Digital IQ Level)
|  | Path Configuration Get | O | 3.2.9 / 3.2.10 |  | Path Configuration IE(Start Frequency, Tx Atten, Rx Atten)
|  |  | O |  |  | Path Control IE(Path Enable/Disable)
|  |  | O |  |  | Antenna Path Delay IE(Tx Delay, Rx Delay)
|  |  | O |  |  | Dynamic PA On/Off IE(Dynamic PA On/Off)
|  |  | O |  |  | Antenna Port Control per Path IE(Antenna Port Role - Antenna Port + ALD pwer feeding / AISG signal) Bias-T
|  | Path Status | O | 3.2.11 / 3.2.12 |  | Path Status IE(Reference Signal Number, Temperature, Tx RF Power, RU Gain, Return Loss)
|  |  | O |  |  | PIM Detection and Cancellation IE(PIM power, PIM cancelled level)
|  | CPRI Configuration Get | O | 3.2.13 / 3.2.14 |  | CPRI Configuration IE(IQ Mapping)
|  |  | O |  |  | CPRI Compression IE(CPRI Compression On/Off, CPRI Compression Ratio)
|  | CPRI Status |  | 3.2.15 / 3.2.16 |  | CPRI Status IE(Connection Validity Check(CVC) value)
|  |  | O |  |  | Optic Information IE(Tx Optic Power, Rx Optic Power, Tx Optic Wave Length, Rx Optic Wave Length, Manufacture Date, Product Number, Vendor Name, Serial Number, Link length of sigle mode fiber(km), Link length of single mode fiber, Link length of 62.5um OM1 fiber, Link length of 50um OM2 fiber, Link length of 50um OM3 fiber, Link length of copper or direct attach cable, Temperature of optic module, Nominal rate)
|  |  | O |  |  | Optic Delay IE(Optic Delay - Round Trip Delay, Toffset, DL Hopping Delay, UL Hopping Delay, Tx Delay-including RU proc delay, Rx Delay - including RU proc delay, Tx Delay - excluding RU proc delay, Rx Delay - excluding RU proc delay)
|  |  | O |  |  | CPRI Compression IE(CPRI Compression On/Off, CPRI Compression Ratio)
| Others | Cell Status Information | O | 3.20.1 / 3.20.2 |  | Cell Status Information IE(Cell Status - enable) DU transmits this message to RU to deliver the status information of cell (Enable/Disable)
|  | Reset | O | 3.5.1 / 3.5.2 |  | Reset Delay IE(Reset Delay)
|  | FA Configuration Delete | O | 3.8.11 / 3.8.12 |  | FA Configuration Delete IE(FA Id, Split Id)
|  | Optic Link Information | O | 3.12.1 / 3.12.2 |  | Optic Delay IE - duplicate with CPRI Status
|  |  | O |  |  | Optic Information IE - duplicate with CPRI Status
|  | Spectrum Analysis Information | O | 3.9.1 / 3.9.2 |  | Path Mode IE(Path Type - Tx/Rx, IQ Data - I/Q, Sample Stream)
|  |  | O |  |  | Power Level IE(Path Type - Tx/Rx, Power Level Data)
|  |  | O |  |  | Total Power Level IE(Path Type - Tx/Rx, FA Power Level)
|  | Antenna Path Delay Setup | O | 3.10.3 / 3.10.4 |  | Antenna Path Delay IE(Tx Delay, Rx Delay)
|  | Dynamic PA Setup | O | 3.19.1 / 3.19.2 |  | Dynamic PA On/Off IE(Dynamic PA On/Off)
|  | PA Bias Change/Power Metering | O | 3.13.1 / 3.13.2 |  | Power metering IE(Command Type)
|  |  | O |  |  | Voltage Change IE(Voltage Change Step)
|  |  | O |  |  | Measured Power IE(Measured Power)
|  | PA Bias Change/Power Metering(Path Based) | O | 3.13.3 / 3.13.4 |  | Power metering IE(Command Type)
| Notification/Ack | Alarm Information Notification/Ack | O | 3.4.1 / 3.4.2 |  | Alarm Data Valid Indicator IE(Valid indicator - not true/true)
|  |  | O |  |  | Alarm IE(Alarm Code, Alarm Subcode Type, Alarm Severity, Alarm Flag, Additional Information)
|  | Alarm Information Request | O | 3.4.3 / 3.4.4 |  | Alarm Data Valid Indicator IE(Valid indicator - not true/true)
|  |  | O |  |  | Alarm IE(Alarm Code, Alarm Subcode Type, Alarm Severity, Alarm Flag, Additional Information)
|  | C&M Path Switchover Notification/Ack | ? | 3.18.1 / 3.18.2
|  | IQ Calibration Notification/Ack | O | 3.22.1 / 3.22.2 |  | Path ID IE
|  | PA Bias Change Complete(Path Based) Noti/Ack | O | 3.13.5 / 3.13.6 |  | Path Voltage Change IE(Voltage Change Step)
| ALD | HDLC Relay | O | 3.14.1 / 3.14.2 |  | Relay Data IE
Interference clearing | Spectrum |  | O
| Spectrogram |  | O
| RSSI |  | O
| Dual Spectrum |  | O
| Dual Spectrogram |  | O
ALD Control | Device Information |  | O
| Alarm Status |  | O
| Tilt |  | O
Coverage Range (check and Optimization) | Signal Generator | CW/E-TM, Source On/Off | O
| Antenna Line Device | Antenna tilt | O
| Alarm Indicator | Alarm Reference, Sound, Volume, Sound Mode | O
Auto Measure
PIM Analyzer | Single Port PIM
Dual Port PIM
Multi Port Wideband PIM

## TimeLine-P1
Person A
Person B
Person C
|  |  |  | March | [6 empty] | April | [21 empty] | May | [21 empty] | June | [19 empty] | July | [22 empty] | August | [20 empty] | September
|  |  |  | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 1 | 2 | 3 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 31 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11
RF Test Plan
Issue & Initial State
| 1 | Functional Specification
| 2 | Test Bench Setup
Samsung RRH purchase & Setup
| 3 | GOM FPGA
| 4 | Device Driver
| 5 | API(GT)
| 6 | Samsung BBU Emulation Measure Menu
Measure Mode & Menu
| 7 | CPRI Link Connection
GOM FPGA, Device Driver including & test
CPRI Link Connection(L1/L2 Setup) & test
API - ALD Control
| 1 | Device Scan Algorithm
Emulator Implementation
| 2 | API
Device Scan
XID negotication(parameter set, connect)
Flow Control
L7 command
Debug & Verification
Installation Verification
| 1 | UI & Menu
| 2 | Initialization Setup
| 3 | Get Information
| 4 | Test & Verification
Carrier Configuration
| 1 | UI & Menu
| 2 | Carrier Setup(Split Mode)
| 3 | Test & Verification
Intererence Clearing
| 1 | Spectrum
UI & Menu
Spectrum Implementation
Debug & Verification
| 2 | Spectrogram
UI & Menu
Spectrogram Implementation
Debug & Verification
| 3 | RSSI
UI & Menu
RSSI Implementation
Debug & Verification
| 4 | Dual Spectrum
UI & Menu
Dual Spectrum Implementation
Debug & Verification
| 5 | Quad Spectrum
UI & Menu
Quad Spectrum Implementation
Debug & Verification
| 6 | Dual Spectrogram
UI & Menu
Dual Spectrogram Implementation
Debug & Verification
RET Control and VSWR
UI & Menu
XID negotiation implementation
L7 command implementation
Debug & Verification
Coverage Range
UI & Menu
Implementation
Debug & Verification
PIM Analysis
| 1 | Single Port Sweep Mode
UI & Menu
Implementation
Debug & Verification
| 2 | Multi Port Sweep Mode
UI & Menu
Implementation
Debug & Verification
| 3 | Multi Port Wideband Mode
UI & Menu
Implementation
Debug & Verification
Auto Measure
UI & Menu
Implementation
Debug & Verification
| 5 | Samsung BBU Emulation Measure Menu
Measure Mode & Menu
| 6 | L1/L2 Setup
CPRI Link Connection
Integration Test
Scanner (Channel / Frequency / Custom)
Functional Specification
This is need to implement all of below things
Meas Create

## TimeLine-without RET
Person A (Sang-Gu Kang)
Person B (Jun-Hong Ahn)
Person C (Sang-Young Jung)
|  |  |  | April |  | May | [21 empty] | June | [19 empty] | July | [22 empty] | August | [20 empty] | September | [18 empty] | October | [20 empty] | November | [20 empty] | December | [20 empty] | January | [19 empty] | February
|  |  |  | 29 | 30 | 1 | 2 | 3 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 31 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 30 | 1 | 2 | 4 | 7 | 8 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 31 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 26 | 27 | 30 | 31 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 28 | 29 | 30 | 31
RF Test Plan
Issue & Initial State
| 1 | Functional Specification
| 2 | Samsung RRH purchase & Setup
| 3 | GOM FPGA, API, and Device Driver Setup
| 4 | SS BBU Emulation Initialization
Measure Mode
CPRI Link Connection
Debug & Verification
API - ALD Control
| 1 | API
Device Scan
XID negotication(parameter set, connect)
Flow Control
L7 command
Debug & Verification
Installation Verification
| 1 | UI & Menu
| 2 | Initialization Setup
| 3 | Get Information
| 4 | Test & Verification
Carrier Configuration
| 1 | UI & Menu
| 2 | Carrier Setup(Split Mode)
| 3 | Test & Verification
Intererence Clearing
| 1 | Spectrum
UI & Menu
Spectrum Implementation
Debug & Verification
| 2 | Spectrogram
UI & Menu
Spectrogram Implementation
Debug & Verification
| 3 | RSSI
UI & Menu
RSSI Implementation
Debug & Verification
| 4 | Dual Spectrum
UI & Menu
Dual Spectrum Implementation
Debug & Verification
| 5 | Quad Spectrum
UI & Menu
Quad Spectrum Implementation
Debug & Verification
| 6 | Dual Spectrogram
UI & Menu
Dual Spectrogram Implementation
Debug & Verification
RET Control and VSWR
UI & Menu
XID negotiation implementation
L7 command implementation
Debug & Verification
Coverage Range
UI & Menu
Implementation
Debug & Verification
PIM Analysis
| 1 | Single Port Sweep Mode
UI & Menu
Implementation
Debug & Verification
| 2 | Multi Port Sweep Mode
UI & Menu
Implementation
Debug & Verification
| 3 | Multi Port Wideband Mode
UI & Menu
Implementation
Debug & Verification
Auto Measure
UI & Menu
Implementation
Debug & Verification
Integration Test
Beta Test(Field)
Scanner (Channel / Frequency / Custom)
Functional Specification
???